## Daily Setup List
Daily Setup List
PDNote field tools · pdnote.app/tools — see the Example and Guide sheet tabs below.
Production
Shooting day / date
Location
Call / first shot target
Meal break
Sunset / location wrap-out
1st AD
Setup order
Setup (scene-shot) | Size / angle | Lens / movement | Action (business / lines) | Cast | Priority | Est. (min) | Target time | Done at | Status | Notes
Total
List setups in shooting order. Wide to tight, and finishing one direction before turning around, is common, but sun, cast availability and location limits change it. Fill target times by adding estimates to the first-shot target, compare with done times, and know before lunch how far behind you are. If behind, agree with the director and producer which “nice” setups to combine or move.
Wrap-up
First shot (actual)
Camera wrap
Moved setups / scenes (next day)
In PDNote scheduling, unshot scenes move to another day and partly shot scenes split their remaining pages before the next call sheet is published. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Example
Daily Setup List — example
Filled in for the fictional drama “The Temperature Between Us”. All people, companies and numbers are made up.
Production | The Temperature Between Us
Shooting day / date | Day 3 · 2026-11-13
Location | Café Ondo (interior)
Call / first shot target | 07:00 · 08:30
Meal break | 12:30
Sunset / location wrap-out | 17:20 · 21:00
1st AD | Jihu Seo
Setup order
Setup (scene-shot) | Size / angle | Lens / movement | Action (business / lines) | Cast | Priority | Est. (min) | Target time | Done at | Status | Notes
7-1 | Wide · from the door | 35mm · locked | Minjun enters, sits by the window, orders | Sua, Jaehoon, Minjun | Must | 40 | 9:10 | 9:20 | Done
7-2 | Mid · Minjun | 50mm · slider | Whole order exchange | Minjun | Must | 30 | 9:40 | 10:05 | Done
2-3 | Insert · apron | 85mm · locked | Sua ties her apron | Sua | Nice | 15 | 11:50 |  | Moved | With scene 14 on Day 4
Total
List setups in shooting order. Wide to tight, and finishing one direction before turning around, is common, but sun, cast availability and location limits change it. Fill target times by adding estimates to the first-shot target, compare with done times, and know before lunch how far behind you are. If behind, agree with the director and producer which “nice” setups to combine or move.
Wrap-up
First shot (actual) | 08:35
Camera wrap | 20:40
Moved setups / scenes (next day) | 2-3 insert → Day 4
In PDNote scheduling, unshot scenes move to another day and partly shot scenes split their remaining pages before the next call sheet is published. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Guide
How to fill in: Daily Setup List
What goes in each field and how to write it. See the Example sheet for a filled-in copy.
What it is for
A daily setup list is the 1st AD’s running order of camera setups for the day, with an estimate and target time for each. Camera and lighting can prepare the next setup early, and the AD can compare actual finish times to see how far behind the day is.
When to use it
Build it with the director and DP once the call sheet is out, hand it round at call, and fill in done times and status as each setup wraps.
Field by field
Field | What | How | Example
Call / first shot target | General call and the time you aim to roll the first take | Match the call sheet; target times start from here. | 07:00 · 08:30
Setup (scene-shot) | Scene and shot number | Join them as on the slate, e.g. 7-1. | 7-2
Priority | Whether the setup is essential | Must or Nice. “Nice” setups are what you combine or move when behind. | Must
Est. (min) | Time from setup to last take | Minutes only; the total adds up. Recalibrate after the first week. | 30
Target time | When you aim to finish the setup | Add each estimate in turn to the first-shot target. | 09:40
Done at | When the setup actually finished | Write it as soon as the last take is called; the gap to target is how far behind you are. | 10:05
Status | Whether the setup is finished | Done, Partial or Moved; note where moved setups went. | Moved
Tips
· Compare target and done times before lunch; the earlier you know, the more options you have.
· Group setups facing the same way and flag turnarounds in the notes.
· When the order changes, update the list and announce it on the radio.
Common mistakes
· Estimates cover takes but not lighting and setup time, so the day slips by mid-morning.
· Window or exterior setups are scheduled after sunset.
· Moved setups are not recorded and drop off the next call sheet.