## Delivery Checklist
Delivery Checklist
PDNote field tools · pdnote.app/tools — see the Example and Guide sheet tabs below.
Production / episode / version
Recipient / contact
Spec version / received on
Delivery date / method (transfer / media)
Area | Item | Spec value | Actual value | Done | Owner | Notes
Picture master
| Resolution |  |  | □
| Frame rate |  |  | □
| Codec / file format |  |  | □
| Aspect ratio |  |  | □
| Colour space / gamma |  |  | □
| Head build (black, bars, countdown, etc.) |  |  | □
| Duration / start timecode |  |  | □
| Textless version |  |  | □
Audio (full mix, stems, M&E)
| Channel configuration |  |  | □
| Track layout |  |  | □
| Loudness standard |  |  | □
| Full mix |  |  | □
| Stems (dialogue / music / effects) |  |  | □
| M&E (music and effects without dialogue) |  |  | □
Subtitles
| Subtitle files (per language / format) |  |  | □
| Subtitles for the deaf and hard of hearing |  |  | □
| On-screen text translation list |  |  | □
| Subtitle sync check |  |  | □
Theatrical (DCP & KDM)
| DCP (aspect ratio / sound configuration) |  |  | □
| KDM target screens / validity |  |  | □
| Test screening check |  |  | □
Publicity & extras
| Stills |  |  | □
| Poster / key art |  |  | □
| Trailer |  |  | □
| Synopsis / credit list |  |  | □
| Music cue sheet |  |  | □
| Rights documents (licence copies) |  |  | □
QC record
| QC report (timecode / issue / fix) |  |  | □
| Re-check of fixed issues |  |  | □
| Redelivery date |  |  | □
| Recipient QC pass confirmed |  |  | □
Archive
| Original camera data, sound files |  |  | □
| Edit project, EDL, XML |  |  | □
| Final master, stems, subtitles |  |  | □
| Documents (contracts, cue sheets, licences) |  |  | □
| Copy locations 1 / 2 / 3 |  |  | □
| Checksum files |  |  | □
Copy each value from the recipient’s delivery specification (broadcaster, platform or distributor) into the spec column. Values differ by recipient, so none are pre-filled. If an actual value differs, agree it with the recipient before delivery.
Put post and delivery dates on the PDNote production schedule as milestones to see them alongside shooting days. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Example
Delivery Checklist — example
Filled in for the fictional drama “The Temperature Between Us”. All people, companies and numbers are made up.
Production / episode / version | The Temperature Between Us · Ep 1–8 · final v2
Recipient / contact | ○○ Platform content operations · Seoyeon Park
Spec version / received on | Delivery spec v3 · 2027-01-08
Delivery date / method (transfer / media) | 2027-02-26 · file transfer + 1 external drive
Area | Item | Spec value | Actual value | Done | Owner | Notes
Picture master
| Resolution | Spec clause 3.1 value | Matches spec | ■ | Dain Choi (DI)
| Frame rate | Spec clause 3.1 value | Matches spec | ■ | Dain Choi (DI)
| Codec / file format | Spec clause 3.2 value | Matches spec | ■ | Dain Choi (DI)
| Aspect ratio |  |  | □
| Colour space / gamma |  |  | □
| Head build (black, bars, countdown, etc.) |  |  | □
| Duration / start timecode |  |  | □
| Textless version |  |  | □
Audio (full mix, stems, M&E)
| Channel configuration |  |  | □
| Track layout |  |  | □
| Loudness standard | Spec clause 4.3 value | Meets spec per measurement report | ■ | Minho Jung (mix) | Report per episode attached
| Full mix |  |  | □
| Stems (dialogue / music / effects) |  |  | □
| M&E (music and effects without dialogue) | Spec clause 4.5 value | Ep 3 some effects missing | □ | Minho Jung (mix) | Fixed version due 2027-02-20
Subtitles
| Subtitle files (per language / format) | Spec clause 5.1 value | Korean and English ready | ■ | Jisu Han (subtitles)
| Subtitles for the deaf and hard of hearing |  |  | □
| On-screen text translation list |  |  | □
| Subtitle sync check |  |  | □
Theatrical (DCP & KDM)
| DCP (aspect ratio / sound configuration) |  |  | □
| KDM target screens / validity |  |  | □
| Test screening check |  |  | □
Publicity & extras
| Stills |  |  | □
| Poster / key art |  |  | □
| Trailer |  |  | □
| Synopsis / credit list |  |  | □
| Music cue sheet |  |  | □
| Rights documents (licence copies) |  |  | □
QC record
| QC report (timecode / issue / fix) |  | Internal QC: 12 notes, 11 fixed | ■ | Dain Choi (DI) | 1 open in Ep 6
| Re-check of fixed issues |  |  | □ | Dain Choi (DI) | Ep 6 fix to be rechecked
| Redelivery date |  |  | □
| Recipient QC pass confirmed |  |  | □
Archive
| Original camera data, sound files |  |  | □
| Edit project, EDL, XML |  |  | □
| Final master, stems, subtitles |  |  | □
| Documents (contracts, cue sheets, licences) |  |  | □
| Copy locations 1 / 2 / 3 |  | Post server · drive A · office drive B | ■ | Geonyoung Lee (production)
| Checksum files |  | Checksums verified for each copy | ■ | Geonyoung Lee (production)
Extra request | Trailer per episode (incl. textless) | Per recipient’s email request |  |  | Hana Kim (production manager) | Requested by email 2027-01-20
Copy each value from the recipient’s delivery specification (broadcaster, platform or distributor) into the spec column. Values differ by recipient, so none are pre-filled. If an actual value differs, agree it with the recipient before delivery.
Put post and delivery dates on the PDNote production schedule as milestones to see them alongside shooting days. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Guide
How to fill in: Delivery Checklist
What goes in each field and how to write it. See the Example sheet for a filled-in copy.
What it is for
A delivery checklist matches every value in the recipient’s delivery specification against the actual files before the finished programme goes to a broadcaster, platform or distributor. Post and production share one sheet showing what is done and what is left, so redeliveries are fewer.
When to use it
Copy the spec values in the day the specification arrives, then fill in actual values and the done column as mastering, subtitling and QC finish. Scan for empty done boxes one last time just before delivery.
Field by field
Field | What | How | Example
Production / episode / version | Exactly what is being delivered | Include the episode range and version name (final v2, for example) so repeat deliveries are easy to tell apart. | The Temperature Between Us · Ep 1–8 · final v2
Recipient / contact | The receiving company and the person handling it | Add the team name so it is clear who to ask. | ○○ Platform content operations · Seoyeon Park
Spec version / received on | Which edition of the specification you worked to | Specs change mid-project. Recording the version and date shows later which standard you matched. | Delivery spec v3 · 2027-01-08
Delivery date / method (transfer / media) | When and how the delivery goes | Say whether it is a file transfer, physical media or both. | 2027-02-26 · file transfer + external drive
Area | The group an item belongs to | Pre-filled items sit under their group heading, so leave this blank for them. Fill it only when adding a row, for example “Extra request”. | Extra request
Item | The deliverable element to check | Keep the pre-filled items and add anything else the recipient asks for in the blank rows. Mark items that do not apply as “n/a” in notes. | Resolution
Spec value | The value the recipient’s spec requires | Copy the spec wording as written and add the clause number. Values differ by recipient, so never guess. | Spec clause 3.1 value
Actual value | The value you checked in the delivery file | Use file info or a measurement report. If it differs from the spec, agree it with the recipient before delivery. | Matches spec (measurement report attached)
Done | Whether spec and actual have been checked against each other | Change it to ■ only after checking it yourself. Leave it blank if it is only “probably fine”. | ■
Owner | Who is responsible for the item | Name the person who checked it; for an outside post house, add the company. | Dain Choi (DI)
Notes | Agreements, open work, file locations | If the recipient agreed an exception, record who agreed it and when. | Ep 6 fix to be rechecked
Tips
· Fill in every spec value as soon as the spec arrives — knowing the values before post work starts avoids re-outputs.
· The recipient’s own specification is the reference. Do not reuse values from this template or a past show, and get unclear values confirmed in writing by the recipient.
· For measured items such as loudness or colour space, put the measurement report file name in notes so you can answer recipient QC questions straight away.
· Use one sheet per recipient. Mixing recipients on one sheet makes it unclear whose standard each value is.
· When QC notes come back, log timecode and fix under QC record and keep the done box empty until the fix has been rechecked.
Common mistakes
· Copying spec values from a previous show, then redelivering because the recipient’s standard differs.
· Working to an old spec after the recipient has issued a new version.
· Ticking boxes without opening the files, and finding a missing textless version or subtitle drift after delivery.
· Finishing the checklist with archive copies in only one place. List copy locations that are physically separate.