## Day Out of Days
Day Out of Days
PDNote field tools · pdnote.app/tools — see the Example and Guide sheet tabs below.
Production
Shooting period
Version / date
Prepared by
Cast by shooting day
Character | Cast | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Work days | Hold days | Total days
Date
Codes: SW start work, W work, WF work finish, SWF start-work-finish (one day), H hold (no shooting but held), T travel. Write dates across the first row, and mark days between first and last work as H to show a continuous engagement. Work days count codes containing W; total days count every marked day. Beyond 20 days, copy the sheet and renumber the header from 21.
In PDNote, assigning scenes to days on the stripboard builds the day out of days for each character and flags clashes with cast unavailability. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Example
Day Out of Days — example
Filled in for the fictional drama “The Temperature Between Us”. All people, companies and numbers are made up.
Production | The Temperature Between Us
Shooting period | 2026-11-11 ~ 2026-11-21 (days 1–10)
Version / date | v2 · 2026-11-05
Prepared by | Seoyun Lee (AD dept.)
Cast by shooting day
Character | Cast | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Work days | Hold days | Total days
Date |  | 11/11 | 11/12 | 11/13 | 11/14 | 11/15 | 11/17 | 11/18 | 11/19 | 11/20 | 11/21
Jaehoon | Hangyeol Oh | SW | W | W | H | W | WF
Minjun | Doyun Park |  |  | SW | W | H | H | W | WF
Codes: SW start work, W work, WF work finish, SWF start-work-finish (one day), H hold (no shooting but held), T travel. Write dates across the first row, and mark days between first and last work as H to show a continuous engagement. Work days count codes containing W; total days count every marked day. Beyond 20 days, copy the sheet and renumber the header from 21.
In PDNote, assigning scenes to days on the stripboard builds the day out of days for each character and flags clashes with cast unavailability. pdnote.app
PDNote field template — downloaded from pdnote.app/tools. Feel free to adapt it.

## Guide
How to fill in: Day Out of Days
What goes in each field and how to write it. See the Example sheet for a filled-in copy.
What it is for
A day out of days (DOOD) shows, for each character, which shooting days are start, work, hold and finish, on one grid. It sizes cast engagements and fees and anchors scheduling talks with agents.
When to use it
Build it once the first stripboard schedule exists, and reissue it with a new version and date whenever the schedule changes. Send only the latest version to cast and production.
Field by field
Field | What | How | Example
Version / date | Which issue of the sheet this is | Bump the version every time the schedule changes and put it in the file name too. | v2 · 2026-11-05
1 | What the character does on day 1 | SW start work, W work, WF work finish, SWF one day only, H hold, T travel; leave blank if not called. Days 2–20 work the same way. | SW
Work days | Days actually shooting | Excel counts codes containing W (SW, W, WF, SWF). | 4
Hold days | Days held without shooting | Mark gaps between first and last work as H and Excel counts them. Fewer holds save cast time and cost. | 2
Tips
· Where a character’s first and last days are far apart, check the stripboard for ways to cut holds.
· Gather one-day (SWF) characters scattered across days into a single day where possible.
· Shade changed cells when you reissue so agents see what moved.
Common mistakes
· Gaps between first and last work are left blank, so real holds are not counted.
· The schedule changes but the old DOOD keeps circulating.
· No dates across the top, so day numbers alone do not say when.